## Project Phases & Tasks
Image Retrieval RAG System — Project Phases & Tasks
End-to-end task breakdown by phase, owner, priority and status
Phase | Task ID | Task Name | Description | Owner | Priority | Status | Dependencies | Notes
Phase 1 Project Setup | T-01 | Environment Setup | Create virtual environment, install all dependencies from requirements.txt | Developer | High | Done | — | Python 3.12 required
Phase 1 Project Setup | T-02 | Configuration Management | Create .env file with GROQ_API_KEY, GROQ_MODEL, TEMPERATURE, IMAGES_DIR, DB paths | Developer | High | Done | T-01 | Never commit .env to git
Phase 1 Project Setup | T-03 | Docker Setup | Validate Dockerfile and compose.yml; test container build and startup | DevOps | Medium | Done | T-01 | Exposes port 8000
Phase 2 Data Preparation | T-04 | Image Collection | Gather and curate source images (charts, photos, objects) into images/ directory | Data Team | High | Done | T-01 | Supports JPEG, PNG
Phase 2 Data Preparation | T-05 | Metadata Authoring | Write caption, tags, data (structured), and inference fields for each image | Data Team | High | Done | T-04 | Stored in db_metadata.pkl
Phase 2 Data Preparation | T-06 | FAISS Index Build | Generate CLIP embeddings for all images and build FAISS index (db_index.faiss) | ML Engineer | High | Done | T-04, T-05 | ViT-B-32 CLIP model used
Phase 3 Core Backend | T-07 | Retrieval Module | Implement hybrid search: CLIP embedding query → FAISS k-NN → tag boosting | Developer | High | Done | T-06 | retrieval/search.py
Phase 3 Core Backend | T-08 | Online Tag Learning | After each search, persist query term as tag on top-3 results to db_metadata.pkl | Developer | Medium | Done | T-07 | Improves future recall
Phase 3 Core Backend | T-09 | LLM Agent Setup | Configure LangChain agent with ChatGroq, bind image_search_tool and chart_reasoning_tool | ML Engineer | High | Done | T-07 | agent/image_agent.py
Phase 3 Core Backend | T-10 | Image Search Tool | Wrap retrieval module as a LangChain @tool usable by the agent | Developer | High | Done | T-07, T-09 | tools/image_search_tool.py
Phase 3 Core Backend | T-11 | Chart Reasoning Tool | Implement tool that extracts structured data and inference from chart image metadata | Developer | High | Done | T-09 | tools/chart_tool.py
Phase 3 Core Backend | T-12 | Agent Runner | Build agent execution loop: handle tool calls, collect tool results, return final answer | Developer | High | Done | T-09, T-10, T-11 | agent/runner.py
Phase 4 API Layer | T-13 | FastAPI Server | Implement POST /api/search and GET /api/images endpoints; serve static UI and images | Developer | High | Done | T-12 | server.py, port 8000
Phase 4 API Layer | T-14 | API Error Handling | Return structured JSON errors with HTTP 4xx/5xx codes for all failure paths | Developer | Medium | In Progress | T-13 | —
Phase 4 API Layer | T-15 | API Documentation | Enable FastAPI auto-generated docs at /docs and /redoc endpoints | Developer | Low | To Do | T-13 | Auto-generated by FastAPI
Phase 5 User Interface | T-16 | Web UI (HTML/JS) | Build responsive Pinterest-style SPA with search bar, results grid, image masonry | Frontend Dev | High | Done | T-13 | ui/static/index.html
Phase 5 User Interface | T-17 | Streamlit Dashboard | Build interactive Streamlit UI with agent answer display and image grid | Developer | Medium | Done | T-12 | ui/app.py
Phase 5 User Interface | T-18 | CLI Interface | Implement terminal-based interactive query loop for developer testing | Developer | Low | Done | T-12 | app.py
Phase 6 Testing | T-19 | Retrieval Quality Testing | Test search results across diverse query types; validate relevance ranking | QA | High | In Progress | T-07 | Use sample image set
Phase 6 Testing | T-20 | Chart Reasoning Accuracy | Verify agent answers against known chart data; check numerical accuracy | QA | High | In Progress | T-11, T-12 | Ground truth needed
Phase 6 Testing | T-21 | API Integration Tests | Test all API endpoints with valid and invalid inputs; verify response schemas | QA | Medium | To Do | T-13 | Use Postman or pytest
Phase 6 Testing | T-22 | UI Cross-browser Testing | Test web UI in Chrome, Firefox, and Safari on desktop and mobile | QA | Medium | To Do | T-16 | —
Phase 7 Deployment | T-23 | Docker Image Validation | Build Docker image from Dockerfile, run smoke tests inside container | DevOps | High | Done | T-03, T-13 | python:3.12-slim base
Phase 7 Deployment | T-24 | Environment Variable Hardening | Audit all config values; ensure no secrets in image layers or compose.yml | DevOps | High | To Do | T-23 | Security requirement
Phase 7 Deployment | T-25 | POC Demo & Handoff | Conduct stakeholder demo, document known limitations, hand off deliverables | Project Owner | High | To Do | T-19–T-23 | Includes BRD, README

## End-to-End Data Flow
Image Retrieval RAG System — End-to-End Data Flow
Detailed step-by-step flow from user query input to final response delivery
Step # | Stage | Actor / Component | Input | Process / Action | Output | Module / File
1 | User Input | User | Natural language query (text) | User types query in Web UI search bar or Streamlit input field | Query string submitted to frontend | ui/static/index.html ui/app.py
2 | API Request | Web UI / Streamlit | Query string | HTTP POST /api/search with JSON body { "query": "..." } | HTTP request received by FastAPI server | server.py
3 | Agent Invocation | FastAPI Server | Query string | Call agent runner with user query; initialize LangChain agent with message history | Agent loop started | agent/runner.py agent/image_agent.py
4 | LLM Decision | Groq LLM (ChatGroq) | System prompt + user query | LLM decides which tool(s) to call based on query type (visual vs analytical) | Tool call instruction(s): image_search_tool and/or chart_reasoning_tool | agent/image_agent.py agent/prompts.py
5 | Query Embedding | image_search_tool | Query string | Encode query using 4 CLIP prompt templates; average and normalize embeddings | 1536-dim normalized query vector | retrieval/search.py tools/image_search_tool.py
6 | Tag Pre-filter | Retrieval Module | Query terms + metadata | Extract keywords from query; match against image tag lists for fast pre-filtering | Candidate image subset for vector search | retrieval/search.py
7 | Vector Search | FAISS Index | Query vector + candidate set | k-NN similarity search on FAISS index; retrieve top-5 most similar image vectors | Top-5 image IDs with cosine similarity scores | retrieval/search.py db/db_index.faiss
8 | Relevance Boosting | Retrieval Module | Search results + query terms | Add +0.05 score bonus if any query keyword is in an image's tag list | Re-ranked image results with boosted scores | retrieval/search.py
9 | Metadata Lookup | Retrieval Module | Top image IDs | Load full metadata (caption, tags, data, inference) for each top result | List of image metadata dicts with relevance scores | db/db_metadata.pkl
10 | Online Tag Learning | Retrieval Module | Top-3 result IDs + query term | Append query term to tags of top-3 images; atomically persist updated pickle | Updated metadata pickle; improved recall for future identical queries | retrieval/search.py db/db_metadata.pkl
11 | Tool Result Return | image_search_tool | Image metadata list | Format results as tool response string; pass back to LangChain agent loop | ToolMessage with image info appended to message history | tools/image_search_tool.py agent/runner.py
12 | Chart Routing | Groq LLM (ChatGroq) | Tool result + original query | If query is analytical, LLM calls chart_reasoning_tool with image metadata | chart_reasoning_tool invocation | agent/image_agent.py
13 | Chart Data Extraction | chart_reasoning_tool | Image metadata dict | Read pre-extracted data (structured key-value pairs) and inference from metadata | Structured data + inference string for the chart image | tools/chart_tool.py db/db_metadata.pkl
14 | Answer Synthesis | Groq LLM (ChatGroq) | All tool results | LLM synthesizes all retrieved information into a coherent, grounded natural language answer | Final answer string; list of image paths used | agent/runner.py
15 | API Response | FastAPI Server | Answer + image list | Serialize to JSON: { answer, images: [{path, caption, score, ...}] } | HTTP 200 JSON response delivered to client | server.py
16 | UI Rendering | Web UI / Streamlit | JSON response | Render agent answer text; display referenced image cards with captions and scores; refresh image grid | User sees answer + relevant images on screen | ui/static/index.html ui/app.py

## Agent Decision Workflow
LLM Agent Decision Workflow
How the agent chooses tools, handles results, and generates answers
Step | Agent State | Decision / Action | Condition | Tool Called | Next State
1 | IDLE | Receive user query | New query submitted via API | — | PLANNING
2 | PLANNING | Build initial message list | Always | — | PLANNING
3 | PLANNING | Invoke LLM with system prompt + query | Always | ChatGroq.invoke() | DECIDING
4 | DECIDING | Parse LLM response for tool calls | LLM returns tool_calls in response | — | TOOL_CALLING
5 | DECIDING | No tool call — return direct answer | LLM returns plain text (simple greeting or out-of-scope query) | — | DONE
6 | TOOL_CALLING | Call image_search_tool(query) | Query is visual / image-based | image_search_tool | OBSERVING
7 | TOOL_CALLING | Call chart_reasoning_tool(metadata, question) | Query is analytical / data-oriented AND image results contain charts | chart_reasoning_tool | OBSERVING
8 | TOOL_CALLING | Call both tools sequentially | Query requires visual + analytical reasoning | image_search_tool → chart_reasoning_tool | OBSERVING
9 | OBSERVING | Append ToolMessage to message history | Always after tool execution | — | RE-PLANNING
10 | RE-PLANNING | Re-invoke LLM with updated message history | Tool results available; LLM may call more tools or synthesize | ChatGroq.invoke() | DECIDING
11 | DECIDING | LLM decides no more tools needed | Sufficient information gathered | — | SYNTHESIZING
12 | SYNTHESIZING | Generate final natural language answer | All tool results in context | — | RETURNING
13 | RETURNING | Extract answer text + used image paths | Always | — | DONE
14 | DONE | Return { answer, images } to FastAPI | Always | — | IDLE

## API Endpoint Workflow
API Endpoint Workflow
Request/response lifecycle for each FastAPI endpoint
Endpoint | Method | Request Input | Validation | Processing Steps | Success Response | Error Responses | Module
GET / | GET | None | None required | Serve index.html from ui/static/ | 200 OK — HTML page | 404 if file missing | server.py
GET /images/{filename} | GET | filename (path param) | File must exist in IMAGES_DIR | 1. Resolve full path from IMAGES_DIR 2. Stream image file bytes | 200 OK — image binary (JPEG/PNG) | 404 Image not found | server.py
GET /api/images | GET | None | None required | 1. Load db_metadata.pkl 2. Build list of {id, path, caption, tags} 3. Serialize to JSON | 200 OK — JSON array of image metadata | 500 if metadata unreadable | server.py
POST /api/search | POST | JSON body: { "query": string } | 1. query must be non-empty string 2. Max length 512 chars | 1. Validate request body 2. Pass query to agent runner 3. Agent calls tools 4. Collect answer + images 5. Serialize response | 200 OK — JSON: { answer: string, images: [{path, caption, score, tags}] } | 400 — missing/invalid query 422 — validation error 500 — agent/LLM failure | server.py agent/runner.py

## Deployment Workflow
Deployment Workflow
Step-by-step guide for local development and Docker deployment
Step # | Mode | Action | Command / File | Expected Output | Status Check | Notes
1 | Both | Clone / download project | git clone <repo> && cd image_retrieval | Project directory created | ls shows all project files | Or unzip if no git
2 | Local | Create Python virtual environment | python -m venv venv | venv/ directory created | venv/Scripts/activate (Win) venv/bin/activate (Unix) | Python 3.12 required
3 | Local | Activate virtual environment | venv\Scripts\activate (Windows) source venv/bin/activate (Mac/Linux) | Shell prefix changes to (venv) | python --version → 3.12.x | —
4 | Local | Install dependencies | pip install -r requirements.txt | All packages installed | pip list shows langchain, faiss-cpu, open-clip-torch, etc. | ~2-5 min first time
5 | Both | Configure environment variables | Copy .env.example to .env Set GROQ_API_KEY, GROQ_MODEL, TEMPERATURE, IMAGES_DIR, DB paths | .env file populated | cat .env shows all keys set (not committed to git) | GROQ_API_KEY is required
6 | Both | Verify image and database assets | ls images/ → *.jpg, *.png present ls db/ → db_index.faiss, db_metadata.pkl present | Assets confirmed | File sizes > 0 bytes | Rebuild index if missing
7 | Local | Start FastAPI server (local) | uvicorn server:app --host 0.0.0.0 --port 8000 --reload | Server running at http://localhost:8000 | GET http://localhost:8000/ returns HTML | --reload for dev hot-reload
8 | Local | Test API endpoint | curl -X POST http://localhost:8000/api/search \ -H 'Content-Type: application/json' \ -d '{"query":"show me a bar chart"}' | JSON response with answer and images | HTTP 200, answer field non-empty | —
9 | Local | Launch Streamlit UI (optional) | streamlit run ui/app.py | Streamlit app at http://localhost:8501 | Browser opens dashboard | Separate process from FastAPI
10 | Docker | Build Docker image | docker build -t image-retrieval . | Docker image built successfully | docker images shows image-retrieval | ~5-10 min first build
11 | Docker | Start with Docker Compose | docker-compose up | Container starts, server listening on 8000 | Logs show 'Uvicorn running on http://0.0.0.0:8000' | Use -d for detached mode
12 | Docker | Verify container health | docker-compose ps curl http://localhost:8000/api/images | Container status: Up | JSON array of images returned | —
13 | Docker | View logs | docker-compose logs -f | Streaming logs in terminal | No ERROR lines at startup | Ctrl+C to stop streaming
14 | Docker | Stop containers | docker-compose down | Containers stopped and removed | docker-compose ps shows no running containers | Data volumes persist

## Component Interaction Matrix
Component Interaction Matrix
Which components communicate with which. ● = caller → callee relationship
Caller \ Callee | Web UI | Streamlit UI | CLI (app.py) | FastAPI Server | Agent Runner | LLM (ChatGroq) | image_search_tool | chart_reasoning_tool | Retrieval Module | FAISS Index | Metadata (pickle) | CLIP Model | Image Files | Groq API
Web UI | — |  |  | ●
Streamlit UI |  | — |  |  | ●
CLI (app.py) |  |  | — |  | ●
FastAPI Server |  |  |  | — | ● | [5 empty] | ● |  | ●
Agent Runner |  |  |  |  | — | ● | ● | ●
LLM (ChatGroq) | [5 empty] | — | [7 empty] | ●
image_search_tool | [6 empty] | — |  | ●
chart_reasoning_tool | [7 empty] | — |  |  | ●
Retrieval Module | [8 empty] | — | ● | ● | ● | ●
FAISS Index | [9 empty] | —
Metadata (pickle) | [10 empty] | —
CLIP Model | [11 empty] | — | ●
Image Files | [12 empty] | —
Groq API | [13 empty] | —

## Test Cases
Test Cases
Functional and integration test scenarios for validation
TC ID | Category | Test Scenario | Query / Input | Expected Result | Pass Criteria | Priority | Status
TC-01 | Retrieval | Visual image search | show me a dog | Top result is Dog.jpg with high relevance score | score ≥ 0.70; Dog.jpg in top 3 results | High | To Do
TC-02 | Retrieval | Chart image search | bar chart showing population | BarChart.png or Bar2.png in top results | At least one chart image in top 5; score ≥ 0.60 | High | To Do
TC-03 | Retrieval | Ambiguous / broad query | animal | Mixed results: cat, dog, cheetah, owl images returned | All returned images contain animals; no irrelevant images | Medium | To Do
TC-04 | Retrieval | Tag boosting effect | population chart (after TC-02 ran once) | Improved ranking due to online tag learning from TC-02 | Top result score ≥ previous run; chart images ranked higher | Medium | To Do
TC-05 | Chart Reasoning | Numerical question from chart | What was the population of India in 2020? | Agent returns specific numerical value from chart data | Answer contains correct number matching chart metadata | High | To Do
TC-06 | Chart Reasoning | Trend analysis question | What is the trend in the line chart? | Agent describes trend direction using chart inference field | Answer references data values; no hallucination | High | To Do
TC-07 | Chart Reasoning | Comparison question | Which country had the highest population? | Agent compares values from chart data and names top country | Correct country identified; answer grounded in chart data | Medium | To Do
TC-08 | Agent | Tool selection — visual query | what does the coffee look like? | Agent calls image_search_tool only (no chart tool) | Tool call log shows only image_search_tool invoked | High | To Do
TC-09 | Agent | Tool selection — analytical query | what was the increase in India population? | Agent calls image_search_tool then chart_reasoning_tool | Both tools invoked in sequence; answer uses chart data | High | To Do
TC-10 | Agent | No-tool direct answer | hello | Agent responds without calling any tools | Response is greeting; no tool calls in log | Low | To Do
TC-11 | API | Valid search request | POST /api/search { "query": "dog" } | HTTP 200 with answer and images array | answer non-empty string; images is non-empty array | High | To Do
TC-12 | API | Empty query validation | POST /api/search { "query": "" } | HTTP 400 or 422 error response | Non-200 status code; error message in response body | High | To Do
TC-13 | API | Missing query field | POST /api/search {} | HTTP 422 Unprocessable Entity | FastAPI validation error response | Medium | To Do
TC-14 | API | Image listing | GET /api/images | HTTP 200 with array of all indexed images | Array length > 0; each item has id, path, caption fields | High | To Do
TC-15 | API | Image file serving | GET /images/Dog.jpg | HTTP 200 with binary image data | Content-Type is image/jpeg; body is valid image | Medium | To Do
TC-16 | UI | Search via web UI | Type 'cat' in search bar, click Search | Loading spinner appears, then results grid shows cat images | Results appear within 5 seconds; cat images visible | High | To Do
TC-17 | UI | Empty search in web UI | Click Search with empty input | No API call made or error shown | Page does not crash; appropriate feedback to user | Medium | To Do
TC-18 | Deployment | Docker Compose startup | docker-compose up | Container starts; GET / returns 200 | No ERROR in startup logs; curl localhost:8000 succeeds | High | To Do
TC-19 | Deployment | Environment variable injection | Start without GROQ_API_KEY set | Server fails to start with clear error message | Non-zero exit code; error message mentions missing API key | Medium | To Do
TC-20 | Performance | Search latency benchmark | 10 sequential search queries | Each query responds in < 3 seconds | P95 latency ≤ 3s on standard developer hardware | High | To Do